## Sheet1
Hamza Malik 501112545
Risk Management and Analysis
Risk | Description
Sensor Malfunction (Technical Risk) #1 | Critical sensors may fail, leading to inadequate emergency response and potential system failure.
Software Failures (Technical Risk). #2 | Software malfunctions could result in incorrect emergency decision-making, endangering operations.
Cybersecurity Threats (Technical and Business Risk) #3 | Vulnerability to cyber-attacks may compromise system functionality and data integrity.
Interoperability with Existing Systems (Technical Risk) #4 | Difficulty integrating AERS with existing infrastructure could diminish response effectiveness.
Compliance with Aviation and Ground Regulations (Legal and Business Risk) #5 | Non-compliance with regulations could result in legal issues and operational suspension.
Battery and Power Failures (Technical Risk) #6 | Power system failures could lead to AERS shutdowns during critical operations.
Data Privacy Concerns (Legal and Business Risk) #7 | Managing sensitive data could lead to privacy breaches and legal challenges.
Hardware Wear and Tear (Technical Risk) #8 | Deterioration of hardware over time may affect reliability and incur maintenance costs.
User Error (Human Factor Risk) #9 | Misuse or misinterpretation by operators could lead to ineffective or worsened emergency responses.
The Monte Carlo Simulation Results (100 Simulations)
|  | Risk | Risk Probability | Expected Impacts | Expected Risk Factor | Risk Factor Rating | High-Risk Factors | Impact
|  | Sensor Malfunction | 52.5% | 2.55 (Marginal to Critical) | 1.25 | #3/#4 | High (60% - 80%) | 3: Critical
|  | Software Failures | 49% | 2.30 (Marginal to Critical) | 1.19 | #6/#7 | About even (40% - 60%) | 2: Marginal
|  | Cybersecurity Threats | 55.7% | 2.70 (Critical) | 1.4 | #1/#2 | Very High (80% - 100%) | 4: Catastrophic
|  | Interoperability with Existing Systems | 48.2% | 2.20 (Marginal) | 1.16 | #7/#8 | About even (40% - 60%) | 2: Marginal
|  | Compliance with Aviation and Ground Regulations | 56.9% | 2.75 (Critical) | 1.42 | #1/#2 | Very High (80% - 100%) | 4: Catastrophic
|  | Battery and Power Failures | 51.1% | 2.40 (Marginal to Critical) | 1.21 | #5/#6 | High (60% - 80%) | 3: Critical
|  | Data Privacy Concerns | 53.3% | 2.65 (Critical) | 1.35 | #2/#3 | High (60% - 80%) | 3: Critical
|  | Hardware Wear and Tear | 46.8% | 2.15 (Marginal) | 1.1 | #8 | Likely (50% - 60%) | 2: Marginal
|  | User Error | 50.4% | 2.50 (Marginal to Critical) | 1.24 | #4/#5 | High (60% - 80%) | 3: Critical